## Kerne Kanban
Task | Status | Assignee | What | Why | How | Gain | Worst Case
1. Modularize YRE Adapters | Not started |  | Refactor Yield Routing Engine to use modular adapters for external DeFi integrations. | Isolates integrations so external failures don't cascade. Allows rapid addition of new yield sources. | Define a universal `IYieldAdapter` interface and rewrite existing strategy adapters to conform to it. | Highly scalable architecture; adding new strategies takes days instead of weeks. | Interface is too rigid for complex sources. Mitigate with flexible data payloads.
2. Dynamic Hedge Rebalancing Engine V2 | Not started |  | Upgrade hedging bot for dynamic, event-driven rebalancing across multiple CEXs and on-chain venues. | Maximizes capital efficiency and minimizes delta exposure by reacting instantly to volatility. | Implement WebSocket listeners for vault events and integrate with CCXT exchange managers. | Near-perfect delta neutrality with reduced slippage and gas costs. | Logic bug causes over-hedging. Mitigate with hard-coded circuit breakers.
3. Scale Autonomous Institutional Outreach | Not started |  | Expand the outreach bot to target more institutional leads, DAOs, and treasury managers. | Builds a massive TVL pipeline automatically, freeing up time to focus on closing deals. | Refine LLM prompts for personalized messaging and integrate LinkedIn/governance forum data. | Consistent stream of warm institutional leads and early strategic partnerships. | Bot sends hallucinated messages. Mitigate with a human-in-the-loop approval step.
4. Finalize Privacy Policy & ToS | Not started |  | Review, finalize, and publish legal documents governing user interaction with Kerne. | Protects the team from liability and clearly defines Kerne as software, not a financial institution. | Review existing drafts for cross-chain/DAO edge cases and integrate mandatory acceptance flows. | Robust legal shield that deters lawsuits and provides clarity to institutional users. | Loophole exposes us to liability. Mitigate by adhering to established DeFi legal templates.
5. Cross-Chain Messaging Abstraction | Not started |  | Create a unified smart contract interface abstracting specific cross-chain protocols (LayerZero, CCIP). | Removes single points of failure. Allows seamless switching or multi-routing of messages. | Design an `IMessageRelay` interface and implement adapters for major messaging protocols. | Unparalleled resilience against bridge hacks, ensuring protocol solvency across chains. | Vulnerability in the abstraction layer. Mitigate through rigorous formal verification.
6. Automated Risk Scoring Oracle | Not started |  | Build an off-chain service to continuously evaluate and score the risk of external yield sources. | Quantifies risk in real-time to safely route capital and rapidly exit deteriorating strategies. | Develop a service aggregating DeFiLlama/security data to calculate scores and update on-chain caps. | Institutional-grade risk management preventing catastrophic losses from external exploits. | Oracle misses a novel exploit. Mitigate by maintaining conservative allocation caps.
7. Pre-Deposit 'Points' Campaign | Not started |  | Design and implement a pre-launch campaign where users deposit assets to earn 'Kerne Points'. | Bootstraps initial TVL and community momentum, allowing us to gauge actual market demand. | Design point emission logic, deploy a secure escrow contract, and build a frontend leaderboard. | Tens of millions in committed TVL before launch, ensuring deep peg stability and social proof. | Escrow contract vulnerability. Mitigate with extremely simple logic and multiple audits.
8. Multi-Sig Operational Security | Not started |  | Transition all admin rights and treasury funds to a strict multi-signature setup. | Eliminates single points of failure in key management, protecting against compromised keys. | Set up Safe contracts with a 3-of-4 threshold using hardware wallets and document strict procedures. | Security posture meeting institutional requirements, eliminating key-person risk. | Loss of multiple hardware wallets. Mitigate with geographically distributed encrypted backups.
9. Real-Time On-Chain Analytics | Not started |  | Develop public dashboards displaying real-time metrics on TVL, kUSD supply, and yield allocations. | Radical transparency builds unbreakable trust and proves solvency to data-driven investors. | Write SQL queries on Dune Analytics and build a dedicated 'Transparency' page on the frontend. | Powerful marketing asset proving kUSD is fully backed and generating sustainable yield. | Data indexing error causes panic. Mitigate by cross-referencing data and adding disclaimers.
10. Optimize ZIN Solver | Not started |  | Upgrade the ZIN Solver to capture intents across multiple venues (1inch Fusion, LI.FI, Aori). | Maximizes spread capture and revenue by accessing the deepest liquidity and highest intent volume. | Refactor solver for modular venue adapters and update settlement logic for specific platform needs. | Significantly increased daily protocol revenue, establishing Kerne as a dominant solver. | Settlement logic vulnerability leads to lost gas. Mitigate by testing on mainnet forks.
11. Co-Marketing Playbooks | Not started |  | Create standardized marketing strategies for when new protocols integrate kUSD. | Ensures maximum TVL and brand awareness extraction from every partnership. | Draft a playbook detailing timelines for announcements, Spaces, blogs, and shared campaigns. | Massive multiplier effect on user acquisition by leveraging partners' existing audiences. | Partner executes poorly, causing brand confusion. Mitigate by requiring mutual approval.
12. ZK-Proof Solvency Attestation | Not started |  | Implement a cryptographic system generating ZK-proofs to verify off-chain CEX assets back kUSD. | Bridges the trust gap between on-chain transparency and off-chain hedging without revealing secrets. | Integrate a ZK-coprocessor or oracle network to verify exchange balances via read-only APIs. | Neutralizes 'FTX risk' narrative, unlocking capital from security-conscious institutions. | Proof generation fails during volatility. Mitigate with redundant attestation methods.
13. Ambassador Program Framework | Not started |  | Design a structured program to recruit and incentivize community ambassadors. | Organic growth is more sustainable than paid ads. Allows rapid expansion into new markets. | Create a tiered reward system (KERNE tokens), set up Discord channels, and track monthly KPIs. | Decentralized marketing army generating continuous social proof and user onboarding. | Ambassadors use spammy tactics. Mitigate with strict brand guidelines and zero-tolerance policies.
14. Cross-Chain Liquidity Monitoring | Not started |  | Build a system tracking kUSD liquidity pool depth across all chains and alerting on critical drops. | Deep liquidity is essential for peg stability. Proactive monitoring prevents depeg events. | Write a script querying DEX subgraphs for balances and integrate with an AlertManager. | Rock-solid peg across all chains, preventing arbitrageurs from exploiting thin order books. | Monitoring fails silently. Mitigate by running redundant instances and daily health checks.
15. Institutional Client Documentation | Not started |  | Create a comprehensive documentation suite tailored for institutional investors and DAO treasuries. | Institutions require detailed risk and legal info. Ready documentation speeds up large allocations. | Write detailed PDFs covering architecture, hedging, risk parameters, and custody integrations. | Drastically reduced sales cycle for institutional clients, signaling competence and reliability. | Documentation becomes outdated. Mitigate by integrating updates into the deployment pipeline.
16. MEV Protection Layer | Not started |  | Integrate MEV protection into core vaults and keeper bots to prevent front-running. | Protects execution, preserving capital efficiency and retaining maximum yield for users. | Route transactions through private RPCs (Flashbots) and implement slippage/deadline checks. | Saves hundreds of thousands in lost value, translating to higher APYs for kUSD holders. | Private RPC fails during liquidation. Mitigate with fallback logic to public mempools.
17. Yield Mechanics Educational Content | Not started |  | Produce blog posts, threads, and videos explaining exactly how Kerne generates yield. | Demystifies complex strategies, building trust and overcoming skepticism of yield-bearing stables. | Break down complex strategies into understandable concepts and publish across multiple platforms. | Establishes Kerne as a thought leader, continuously converting skeptical users into depositors. | Oversimplification leads to inaccuracy. Mitigate by having engineering review all content.
18. Decentralized Keeper Network | Not started |  | Transition routine maintenance tasks (harvests, liquidations) to a decentralized network (Gelato). | Removes centralized points of failure, ensuring protocol autonomy if internal infrastructure fails. | Write resolver contracts defining execution conditions and configure tasks on the decentralized network. | True protocol autonomy and censorship resistance, strengthening regulatory positioning. | Network outage prevents critical liquidations. Mitigate by keeping internal bots as a fallback.
19. Tiered Liquidity Mining Structure | Not started |  | Design a KERNE emission schedule rewarding long-term capital lockups with higher multipliers. | Flat schedules attract mercenary farmers. Tiers acquire sticky, long-term TVL that stabilizes Kerne. | Model emission curves and multiplier tiers, then implement them into staking smart contracts. | Highly loyal depositor base and reduced circulating supply, creating upward price pressure. | Lockups are too restrictive. Mitigate by offering a liquid option with base emissions.
20. Incident Response Playbook | Not started |  | Create a step-by-step manual for responding to crises (exploits, depegs, outages). | Prevents panic and indecision. Ensures rapid execution of emergency pauses and communication. | Draft emergency contacts, communication templates, and technical steps for pausing contracts. | Drastically reduced response times, potentially saving millions and maintaining community trust. | Playbook is too rigid. Mitigate by designing it as a flexible framework, empowering judgment calls.
21. 'Kerne Alpha' Twitter Spaces | Not started |  | Initiate a weekly live audio show discussing DeFi trends, yield strategies, and protocol updates. | Builds parasocial connections, shapes the narrative, and cross-pollinates audiences with partners. | Schedule Spaces, secure guests from partner protocols, co-host, and repurpose audio into clips. | Rapid Twitter growth, establishing Kerne as a DeFi alpha hub and converting listeners to users. | Accidental regulatory misstep live. Mitigate with clear talking points and avoiding price talk.
22. Optimize Docker & Serverless | Not started |  | Audit and upgrade deployment architecture, moving Yield Server to serverless and optimizing bots. | Ensures infrastructure handles massive traffic spikes without latency as TVL grows. | Refactor Yield Server to use Edge Functions and streamline Dockerfiles for faster bot deployment. | 99.99% uptime and sub-second response times, ensuring flawless UX and hedging operation. | Migration misconfiguration causes an outage. Mitigate with blue-green deployments and staging.
23. RWA Collateral Target List | Not started |  | Research and compile a strategic list of RWA protocols to accept as collateral for kUSD. | Diversifying into RWAs provides a stable yield floor during crypto bear markets. | Analyze top RWA protocols based on TVL, legal structure, and security, then initiate BD talks. | Positions Kerne as a bridge between TradFi yields and DeFi, attracting risk-averse capital. | Integrating a non-compliant RWA. Mitigate by strictly limiting caps and partnering with compliant issuers.
24. Discord/Telegram Gamification | Not started |  | Integrate bots and leveling systems to reward users for active community participation. | Engaged communities defend against competitors and can be mobilized for marketing/governance. | Configure tools to track activity, assign roles/XP, and tie them to tangible protocol benefits. | Vibrant, self-sustaining community that educates new users and reduces the support burden. | Incentivizes spam. Mitigate by rewarding quality over quantity and empowering human moderators.
25. Weekly 'State of Kerne' Reports | Not started |  | Publish a detailed weekly report summarizing TVL, yield, hedging PnL, and milestones. | Radical transparency maintains trust during downturns, showing exactly what's under the hood. | Automate data extraction from dashboards and format it into a digestible newsletter with commentary. | Unparalleled reputation for honesty, becoming required reading for institutional investors. | Report shows temporary underperformance. Mitigate by providing clear context and corrective actions.
26. Beta Tester Feedback Loop | Not started |  | Create a structured process for gathering and acting upon feedback from early testnet users. | Ensures we build a product people want to use, allowing rapid UI/UX pivots before mainnet. | Set up private channels/forms for testers and review feedback weekly to prioritize improvements. | Highly polished, intuitive product that reduces friction during the critical initial TVL ramp-up. | Overwhelmed by conflicting feedback. Mitigate by ruthlessly prioritizing based on strategic goals.
27. Decentralized Risk Committee | Not started |  | Conceptualize a DAO sub-committee of experts to evaluate and approve new yield strategies. | Distributes power, satisfying regulatory requirements and empowering the community. | Draft a governance mandate defining elections, compensation, and slashing mechanics for bad approvals. | Scalable risk management leveraging community intelligence, allowing rapid strategy integration. | Committee captured by malicious actors. Mitigate by requiring high stakes and DAO veto power.
28. Refine Invariant Testing Strategy | Not started |  | Design a targeted invariant testing suite using tools like Echidna or Medusa for KerneVault. | Mathematical certainty of core logic is non-negotiable for confidently deploying upgrades. | Write specific, bounded invariant properties and configure continuous fuzzing campaigns. | Highest possible smart contract security, reducing external audit costs and exploit probability. | Fuzzing misses a complex vulnerability. Mitigate by combining with manual audits and bug bounties.
29. ZIN Tokenomics Smart Contracts | Not started |  | Implement contracts governing the KERNE token (vesting, buy-and-burn, revenue-sharing). | Tokenomics are the economic engine. Flawless implementation aligns incentives and drives growth. | Write the ERC-20 contract, timelocked vesting wallets, and the revenue fee-splitter contract. | Robust economic system creating persistent buy pressure and maximizing fully diluted valuation. | Bug allows claiming unearned tokens. Mitigate by using OpenZeppelin templates and formal verification.
30. Lending Protocol Integrations | Not started |  | Execute BD strategy to get kUSD listed as collateral on major lending markets (Aave, Compound). | Utility drives demand. Lending integration allows users to leverage kUSD, creating massive organic demand. | Draft governance proposals highlighting kUSD's liquidity/safety and engage delegates for votes. | Unlocks billions in potential TVL through 'double dip' utility, making kUSD highly attractive. | Proposal rejected due to politics. Mitigate by building delegate relationships beforehand.
31. LST/LRT Provider Partnerships | Not started |  | Formalize strategic partnerships with Liquid Staking/Restaking providers (Lido, ether.fi). | Kerne amplifies LST demand. Partnerships allow joint campaigns tapping into massive user bases. | Initiate BD conversations proposing boosted emissions for their collateral in exchange for promotion. | Rapid acquisition of high-quality TVL by aligning with the biggest players in the staking ecosystem. | Partner protocol suffers an exploit. Mitigate by strictly capping exposure to any single LST/LRT.
32. Emergency Pause Mechanisms | Not started |  | Implement granular, role-based access controls allowing instant pausing of specific functions. | Seconds matter during an exploit. Granular pauses halt malicious activity without full shutdowns. | Integrate OpenZeppelin's `Pausable` extension and define roles for the security multisig. | Ultimate safety net preventing total capital loss, mandatory for top-tier audits and institutions. | Pause abused by compromised admin. Mitigate with geographically distributed multi-sig control.
33. Internal Smart Contract Fuzzing | Not started |  | Execute a multi-week internal fuzzing campaign bombarding contracts with randomized inputs. | Finds edge cases before hackers do, allowing quiet fixes before paying external auditors. | Write extensive property-based tests defining core invariants and run them continuously. | Highly secure codebase entering audits, speeding up review timelines and lowering exploit probability. | Fuzzing consumes excessive time without finding bugs. Mitigate by focusing on critical functions.